## Sheet1
Task name | Status | Duration | Start | End | Name | May | [22 empty] | June
[6 empty] | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7
1. Design | Complete | 1 day | 8/6/2022 | 9/6/2022 | All | bar: May 8 to May 9
2. Home | Not yet | 3 days | 10/6/2022 | 12/6/2022 | All | bar: May 10 to May 12
2.1 Navbar | Complete | bar: May 10 to May 12
2.2 Highlight | Complete | bar: May 10 to May 12
2.3 Brand | Complete | bar: May 10 to May 12
2.4 Footer | Complete | bar: May 10 to May 12
2.5 ChatBot | Not yet | [34 empty] | Status | bar: May 10 to May 12
3. Product Detail* | Complete | 7 days | 13/6/2022 | 19/6/2022 | All | [30 empty] | do | bar: May 13 to May 19
3.1 Description | Complete | [34 empty] | Complete | bar: May 13 to May 19
3.2 Network | Complete | [34 empty] | Not yet | bar: May 13 to May 19
3.3 Product highlight | Complete | bar: May 13 to May 19
3.4 Videos | Complete | bar: May 13 to May 19
3.5 Resources | Complete | bar: May 13 to May 19
4. Product | Complete | 3 days | 20/6/2022 | 22/6/2022 | All | bar: May 20 to May 22
4.1 Category | Complete | bar: May 20 to May 22
5. เกี่ยวกับเรา* | Complete | 5 days | 23/6/2022 | 25/6/2022 | Sui | bar: May 23 to May 25
5.1 Award | Complete | bar: May 23 to May 25
6. ข่าวสารและกิจกรรม* | Complete | 3 days | 23/6/2022 | 25/6/2022 | Art | bar: May 23 to May 25
7. ดาวน์โหลด* | Complete | 3 days | 23/6/2022 | 25/6/2022 | Oum | bar: May 23 to May 25
8. บริการ | Complete | 2 days | 26/6/2022 | 27/6/2022 | Sui | bar: May 26 to May 27
9. ติดต่อเรา | Complete | 2 days | 26/6/2022 | 27/6/2022 | Art | bar: May 26 to May 27
10. ร่วมงานกับเรา | Complete | 2 days | 26/6/2022 | 27/6/2022 | Oum | bar: May 26 to May 27
11. login | Complete | 2 days | 28/6/2022 | 29/6/2022 | Oum | bar: May 28 to May 29
12. register | Complete | 2 days | 28/6/2022 | 29/6/2022 | Art | bar: May 28 to May 29
13. รถเข็น | do | 3 days | 30/6/2022 | 2/7/2022 | All | bar: May 30 to June 2
14. ระบบจ่ายเงิน |  | 3 days | 30/6/2022 | 2/7/2022 | All | bar: May 30 to June 2
15. Order history |  | 2 days | 3/7/2022 | 4/7/2022 | Sui | bar: June 3 to June 4
16. Order history detail |  | 2 days | 3/7/2022 | 4/7/2022 | Sui | bar: June 3 to June 4
17. Edit profile |  | 2 days | 3/7/2022 | 4/7/2022 | Oum,Art | bar: June 3 to June 4
17.1 Name | bar: June 3 to June 4
17.2 Chane Password | bar: June 3 to June 4
17.3 Change Address | bar: June 3 to June 4
18. เก็บรายละเอียด |  | 3 days | 5/7/2022 | 7/7/2022 | All | bar: June 5 to June 7